First quarter progress report FY22 – Kleinjan/Kovacs

Soybean Nitrogen fixation under Nitrogen and Sulfur fertilization

Objectives:

1) Estimate BNF and N budgets in soybean considering N and sulfur (S) fertilization rates.

2) Build a predictive model for BNF in the United States using environmental data.

3) Extend the results to soybean growers using local and national extension networks.

Objective 1: Estimate BNF and N budgets in soybean considering N and sulfur (S) fertilization rates.

In 2022, this study was performed at 30 locations in 14 states with Dr. Ignacio Ciampitti of Kansas State University (KSU) serving as the lead PI.  Every effort was made to select a site in each state that was likely to be 1) responsive, and 1) non-responsive to soybean S fertilization.  This study is a continuation of an effort begun in the spring of 2021. If all proposed locations are harvested in 2022, there will be 57 site-years of data.

In South Dakota, the studies were planted in Aurora (theoretical responsive environment) and Brookings (theoretical non-responsive environment).  Plots were planted at both locations in May.  Soil samples were collected prior to planting and N and S fertilizer treatments were surface applied immediately following planting.  Plant and soil samples were collected at the R2, R4, and R6 growth stages.  The soil samples were frozen and deivered to AgVise Labs in Benson, MN.  Soybean whole-plant and stem samples were weighed, dried and course-ground, and will be sent to Dr. Ciampitti’s laboratory at KSU for analysis.  Plots were harvested with a Kincaid plot combine in early October and grain samples will sent to the University of Minnesota (c/o Dr. Seth Naeve) for analysis.  A detailed analysis including yield response to fertilization will be provided in future reports.

Objective 2: Build a predictive model for BNF in the United States using environmental data.

Dr. Ciampitti and his group at KSU will be conducting meta-analysis and attempting to build a predictive model once all the data has been compiled.  Prediction models will likely be national in scope with regional considerations.  Preliminary observations from 2021 suggest that due to the high uncertainty in treatment response and contribution of N fixation on a deficit of soil N, N fertilization is unlikely to increase yields, leading to non-profitable recommendations. Sulfur deficiency, on the other hand, should be explored under site- specific conditions.

Objective 3. Extend results to soybean growers through extension networks.

I plan to summarize South Dakota results and share with growers through winter talks (virtual and in-person), radio interviews, SDSU extension website publications, and social media during the January - March 2023 timeframe.  A national summary fact sheet will be published for the study.  A manuscript titled: ‘Soybean yield response to nitrogen and sulfur fertilization in the United States: contribution of soil N and N fixation processes’ has been submitted to Field Crops Research for publication.