First quarter progress report FY23 – Kleinjan

Evaluating Yield Response and the Return on Investment of Biological Seed Treatments

Objectives:

1) Identify yield response in soybean to biological seed treatments (commonly marketed products).

2) Conduct economic analyses on the value of these products.

3) Extend the results to soybean growers using local and national extension networks.

Objective 1: Identify yield response in soybean to biological seed treatments

In 2022, this study was performed at 60 locations in 17 states with Dr. Laura Lindsey of Ohio State University and Dr. Rachel Vann of North Carolina State University serving as Principal Investigators.  Nine commonly marketed biological seed treatment products from six companies were tested at all locations

In South Dakota, the studies were planted at four locations: Bath, Brookings, Miller, and Renner.  Plots were planted at all locations at normal planting dates in May.  Baseline soil samples were collected at planting time.  Stand counts were taken at the ~V3 growth stage.  Plots were harvested with a Kincaid plot combine in October and grain samples will sent to Ohio State University (c/o Dr. Laura Lindsey) for analysis.  At the time of this report, data has not been analyzed for South Dakota. A detailed analysis including potential yield response to biological products will be provided in future reports.

Objective 2: Conduct economic analyses on the value of these products.

Data has not yet been compiled but Dr. Lindsey has conveyed through personal communication that none of the trial locations submitted so far have had any significant treatment differences.  It is unlikely that any of the products will be found to be economically viable.  A detailed analysis will be included in future reports.

Objective 3. Extend results to soybean growers through extension networks.

I plan to summarize South Dakota results and share with growers through winter talks (virtual and in-person), radio interviews, SDSU extension website publications, and social media during the January - March 2023 timeframe.  A national summary fact sheet and peer-reviewed journal article will be published for the study at a future date.