PROGRESS REPORT - JANUARY/23

Project Title: Effect of feeding high oleic soybean oil to finishing pigs on growth performance, carcass characteristics, and meat quality.

| Principal Investigator: |  | Crystal L. Levesque, PhD – Associate Professor |  |  |
| --- | --- | --- | --- | --- |
| Institution: | South Dakota State University |  |  |  |
| Address: | Animal Science Complex 106, 1097 North Campus Drive |  |  |  |
| City, ST ZIP | Brookings, SD, 57007 |  |  |  |
| Phone: | 605-688-5011 |  | FAX: | 605-688-6170 |
| Email: | crystal.levesque@sdstate.edu |  |  |  |

Project overview

Increasing monounsaturated fatty acid (FA) intake is relevant for human health and represents a current concern for consumers, especially considering the 2020-2021 pandemic. Because of this, there is a growing interest in strategies to improve FA profiles and marbling of pork products by enhancing the amounts of monounsaturated FA. New soybean varieties are producing soybean oil with high oleic acid content (HOSBO), which can be included in swine diets to improve FA profile of pork. Therefore, the objective of this project is to evaluate the effects of dietary high oleic soybean oil supplementation and duration on carcass characteristics and meat quality of finishing pigs. A total of 450 twenty-one-week-old growing pigs housed in 90 pens will be arranged in a 2×2+1 factorial design. Experimental diets include two different fat sources (ANI: CON diet including 4% of animal fat and HOSBO: CON diet including 4% of high oleic soybean oil) each provided at one of two feeding durations (2 or 4 weeks before marketing). A corn-based diet without fat inclusion (CON) will be used as the control/standard commercial diet for comparison. Observations will include pig growth performance, carcass characteristics, FA profile in pork carcass, and a consumer sensory evaluation. Validation of the inclusion of high oleic soybean oil in pig diets to improve pork quality will increase the market potential for soy oil inclusion in swine diets, resulting in higher demand for soybeans.

Project updates

- Animal work

- Experimental diets were formulated and fabricated according to the protocol.

| Ingredient | CON | AN | HOSO |
| --- | --- | --- | --- |
| Corn | 86.76 | 82.61 | 82.62 |
| Soybean meal, 46.5% | 11.00 | 11.00 | 11.00 |
| L-Lysine HCl | 0.20 | 0.26 | 0.26 |
| Threonine Pro80 | 0.077 | 0.121 | 0.119 |
| DL-Methionine | 0.000 | 0.038 | 0.036 |
| L-Tryptophan | 0.003 | 0.012 | 0.012 |
| Choice white grease | 0.00 | 4.00 | 0.00 |
| High oleic soybean oil | 0.00 | 0.00 | 4.00 |
| Monocalcium phosphate | 0.55 | 0.55 | 0.55 |
| Limestone | 0.88 | 0.88 | 0.88 |
| Salt | 0.20 | 0.20 | 0.20 |
| Swine Vitamin premix | 0.05 | 0.05 | 0.05 |
| Swine Mineral premix | 0.15 | 0.15 | 0.15 |
| Swine Larvicide | 0.13 | 0.13 | 0.13 |
| Mixed feed | 100.00 | 100.00 | 100.00 |
| Calculated composition |  |  |  |
| ME, Kcal/kg | 3320 | 3539 | 3523 |
| Crude Protein, % | 12 | 12 | 12 |
| SID Lysine, % | 0.61 | 0.65 | 0.65 |
| Lys:calorie | 1.83 | 1.83 | 1.83 |
| SID Arg, % | 0.60 | 0.59 | 0.59 |
| SID Met, % | 0.19 | 0.22 | 0.22 |
| SID, Met + Cys, % | 0.38 | 0.41 | 0.41 |
| SID THR, % | 0.40 | 0.43 | 0.42 |
| SID TRP, % | 0.11 | 0.12 | 0.12 |
| SID ILEU, % | 0.42 | 0.41 | 0.41 |
| SID LEU, % | 1.06 | 1.03 | 1.03 |
| SID VAL, % | 0.48 | 0.47 | 0.47 |
| SID HIS, % | 0.29 | 0.29 | 0.29 |
| SID PHE, % | 0.52 | 0.50 | 0.50 |
| Calcium, % | 0.46 | 0.46 | 0.46 |
| Phosphorus, % | 0.41 | 0.40 | 0.40 |
| ATTD P, % | 0.18 | 0.18 | 0.18 |
| STTD P, % | 0.21 | 0.21 | 0.21 |
| Sodium, % | 0.11 | 0.11 | 0.11 |
| Ca/P | 1.14 | 1.17 | 1.17 |

- The animal work phase of this project is in progress. By January 30, more than 50% of the work has been completed. A total of 450 growing pigs were housed in 90 pens based on body weight and gender. Pens of pigs were assigned to one of five treatments. Pigs were fed experimental diets for the last four weeks before marketing according to treatments.

- To date, 55 pens (275 pigs) have completed the trial and pigs have been marketing. The remain pens/pigs (35/175) will completr the experimental period by February 21.

- Carcass data collection

From the 60 pigs targeted for carcass data collection, 30 pigs have been harvested and carcass data and tissue samples have been collected according to the protocols.

- Consumer sensory evaluation

Boneless loin samples are being collected for sensory traits evaluation by a consumer sensory panel. These analysis will be performed in partnership with the meat science group at North Dakota State University and there is a opportunity to collaborate with a new faculty member of this group that is an expert in sensory trait evaluation. This individual is available to perform the sensory analysis beginning June 2023. Thus the last piece of this project (sensory analysis) will be completed after the end date of the grant. It is likely we will request a no-cost extension to allow us to capitalize on this opportunity to partner with the NDSU experts. Benefits of this opportunity include:

- The collaborator at NDSU is an expert in sensory traits evaluation, which represents an opportunity to fortify the methods and procedures for this analysis.

- This individual will be leading and supervising the sensory panel evaluation, which ensure the highest quality data collection.

- In addition to supporting data collection, this collaborator will be involved in data analysis and interpretation including the review of communication material from this project (i.e. abstracts, extension articles, pee reviewed papers).

- Student training

At least 6 graduate students have been involved in this trial.  Students have been supporting the live animal phase of this project including daily animal care, data collection, sample collection, animal slaughter and processing.