Minnesota Soybean Research and Promotion Council

# Annual Research Progress Report

# Due November 1st

Audience: This information will be utilized to create a research reporting booklet that will be distributed to growers and crop consultants. This is a great opportunity to communi- cate your research directly to growers. Please keep your producer audience in mind when submitting your report. Reports will be printed in COLOR – please include color figures and photos to help explain your results to growers!

## Project Title: Soybean Breeding and Genetics

Principal Investigator(s): Aaron Lorenz

Project Period: Aug 1 – Oct 31

Research Question/Objectives:

Goal 1: Contribute to the resiliency and economic opportunities of Minnesota soybean growers.

Objective 1: Develop general-purpose and food-type soybean varieties adapted to Minnesota, and new sources of pest and disease resistance for application to Minnesota-adapted varieties.

Goal 2: Provide an unbiased source of information to growers on the relative performance of commercial varieties adapted across Minnesota.

Objective 2: Continue testing public and private soybean varieties available to Minnesota soybean producers.

Goal 3: Contribute to the long-term sustainability of soybean production in the face of new and evolving pests.

Objective 3: Discover and develop new sources of resistance to soybean pests and diseases.

Results: As described in the previous Q1 report, all breeding nurseries and yield trials were successfully planted across the state of MN. In terms of materials in the field for the breeding programs, we planted 72 unique breeding parents and used them to design and successfully make 109 unique breeding crosses. F1 seeds from these crosses were harvested and sent to the Chile winter nursery for generational advancement. This past summer we grew 102 F2 populations and 132 F4 populations. The F2 populations were advanced to the F3 generation by single-seed descent, and F3 seeds were sent to Chile for generational advancement. The F4 were advanced to F4:5 families through individual plant harvest. Individual plant harvests were performed the last quarter and seed is currently being threshed.

Approximately 7000 plant rows were grown this year, and 2200 were selected on the basis of standability and maturity. These were harvested and will go into prelim yield trials next year. Yield trials were harvested across 11 MN locations. Data has been imported into our database and analysis is ongoing as we prepare reports and make selections. All seed increases were harvested on time. The most important seed increase were the purified seed increases which produce breeder’s seed for variety licensing and release. We had six of these at this stage. Over the coming month we will analyze the data and determine which varieties to advance and report this during our Crop Variety Review Committee.

Additionally, we completed the UMN State Soybean Variety Trials and published a preliminary report at https://varietytrials.umn.edu/soybean. A final report is being compiled right now in which we will include composition data.

Application/Use: Creation of novel soybean varieties with high yield, early maturity, and modified composition for increased value.

Materials and Methods: Variety field trials across 11 locations, sexual hybridization between superior parents, and standard breeding methods to derive new varieties from said breeding crosses.

Economic Benefit to a Typical 500 Acre Soybean Enterprise: Creating new soybean varieties with enhanced value, novel pest resistance, and high yield helps producers maximize value per acre. The benefits of creating and choosing new varieties to maximize yield are clear, as on-farm yields have increased over the years. At least half of this on-farm increase in yield can be attributed to development of better varieties. Much of this activity is conducted in the private sector. Our public sector efforts strive to compliment private sector research through licensing of germplasm, pursuant of long-term research, education of future plant breeders, and testing and publication of new breeding methods.