Quarterly Report: July 1, 2024 - September 30, 2024

Soy Aquaculture Alliance

Project Title: Improved Characterization of Soybean Meal Induced Enteritis Using Machine Learning Automation and Standardization to Score Distal Intestinal Histology Slides

Principal Investigator: Dr. Jacob Bledsoe

Organization: University of Idaho

Project Code: 44223

Executive Summary

This quarter has seen advancements in both technical development and team dynamics. Despite the unexpected departure of Dr. Nathan Redman, our lead research scientist, the project continues to progress well with the completion of the ResNet algorithm scripting and the strengthening of our collaborative network through the addition of Dr. Salvatore Frasca, a highly regarded histopathologist.

Q2 Project Activities and Achievements

1.	Staffing Updates:

-Dr. Nathan Redman, our lead research scientist/postdoc, has taken a new position effective September 13th. A broad search for his replacement is already underway, with advertisements placed at key conferences such as Mucosal Health in Aquaculture 2024 and WAS 2024 Copenhagen, as well as on university-related job boards and social media accounts. We are currently reviewing new applicants.

2.	Completion of Machine Learning Framework:

-The machine learning algorithm, ResNet, has been fully scripted, and the computational framework is complete. This ensures that we have a reliable system for processing and analyzing digitized histology slides.

3.	Collaboration and Crowdsourcing:

-Dr. Salvatore Frasca, a skilled and well-respected histopathologist, has agreed to participate in the project. His involvement is crucial for the scoring of digitized slides, particularly following the departure of our initial histopathologist.

-We have had success in crowdsourcing slides, particularly following our advertisement at Mucosal Health Aquaculture 2024 in Porto, Portugal. We have received contact from multiple laboratories interested in sharing slides from Atlantic salmon and trout, which enhances the diversity and volume of our data set.

Challenges and Adjustments

The departure of Dr. Nathan Redman posed a significant challenge this quarter, necessitating a swift and broad-reaching search for a qualified replacement to ensure continuity in our research activities. Additionally, securing a new collaborating histopathologist was successfully accomplished with the involvement of Dr. Frasca, mitigating potential delays in our timeline.

Next Steps

In the next quarter, we will focus on:

- Finalizing the recruitment of a new lead research scientist.

- Scoring of more histology slides with Dr. Frasca.

- Continuing to collect and process histology slides from international collaborators.

- Further testing and refining of the neural network model to ensure its readiness for practical application.

- Optimizing the model to include a pre-training quality assurance/quality control (QA/QC) and image subsampling step. This will ensure that images are not biased and allow the model to effectively subsample each image, enhancing the robustness and accuracy of our analysis.

- Iterative optimization of the ResNet parameters will continue as the model is further trained on ground-truthed histopathologist scored slides.