Summary

In this quarter, administrative progress has been made in addressing previous project delays. A No-Cost Extension (NCE) request was submitted on February 11, 2025 and approved by the Soy Aquaculture Alliance (SAA) on March 18, 2025, extending the project termination date to December 31, 2025. This extension allows for completion of key project objectives, particularly the collection of a sufficiently large and diverse set of histological slides for training the machine learning model. Additionally, a research associate has been hired onto the project to replace the research scientist that left the project in August 2024. The new hire has started working on expanding collaborations to acquire additional samples.

Q1 2025 Project Activities and Achievements

1. No-Cost Extension Approval:

- The project’s NCE request was approved by SAA and is currently being processed by the University of Idaho’s Office of Sponsored Projects.

- The extension was necessitated by delays in hiring a research scientist (who left in August 2024), which subsequently delayed the acquisition of a sufficient number of histological slides from salmonid studies containing both healthy and enteritis-positive individuals.

2. Hiring of Research Associate and Expanded Slide Sourcing Efforts:

- A research associate was hired and has allocated 36% FTE to this project.

- They have begun contacting additional external labs and collaborators to source more histological slides.

- Efforts are being made to ensure the dataset includes a broad representation of salmonid intestinal samples, particularly those capturing a range of enteritis severity.

3. Machine Learning Model Preparedness:

- The slide processing and machine learning model frameworks are complete and prepared for training.

- We are waiting to secure a sufficiently large dataset of slide images to ensure robust training of the model.

Challenges and Adjustments

- Slide Sourcing Delays: While the machine learning framework is ready, the project still requires a larger, high-quality dataset of histology slides for training.

- Hiring Delays: The delayed hiring of a research scientist set back progress on sourcing efforts, though the recent hiring of a research associate has helped mitigate these issues.

Next Steps

- Continue external collaboration efforts to acquire additional histology slides, with a focus on ensuring both healthy and enteritis-positive samples.

- Finalize processing of the NCE through the Office of Sponsored Projects.

- Begin initial training runs of the machine learning model with available histology slide data.

- Evaluate slide dataset gaps and determine if additional sourcing efforts are required before full-scale training can commence.