Annual Progress Report, 2023

Advancing Varietal Resistance to Soybean Cyst Nematode in Minnesota

PIs: Aaron Lorenz and Senyu Chen

Objectives

The objectives of this project and related accomplishments were as follows:

Goals 1. Continue to efficiently produce new SCN-resistant germplasm and varieties and thus expand availability of SCN resistance across all maturity groups grown in Minnesota.

Objective 1. Deploy DNA markers linked to genes conferring SCN resistance to enhance the efficiency and efficacy of breeding for SCN resistance.

During the summer of 2023, nearly all of our 100 crosses included at least one parent specifically targeted for SCN resistance were made. All crosses were successfully made and F1 seed was sent to Chile. F2 seeds were returned in time for planting.

F2, F3, and F4 breeding populations previously targeted for SCN resistance were advanced successfully using winter and summer nurseries per standard operating procedures.

In 2023, we genotyped 4700 plants for SCN resistance and found that 2209 were homozygous resistance. These plants were targeted for harvest and we harvested each selected plant individually.  The seeds from these plants are growing in plant rows this year. Using molecular markers to select which individual plants have SCN resistance greatly enriches our breeding pipeline for SCN resistance. Without this funding to use these markers, we would have a much harder time breeding for SCN resistance.

This is evidenced by the number of SCN resistant breeding lines we enter into regional trials. In 2023, we entered 30 advanced breeding lines. All but two of these lines was determined to in fact have resistant according to a greenhouse bioassay, indicating the effectiveness of our marker program. Many of the resistant lines performed well in terms of yield and overall agronomics. For example, M17-152029 was the highest yielding lines in the MG 0 test.

We are also striving to integrate SCN resistance into our specialty and food type varieties. For example, natto varieties have not typically carried SCN resistance, but with increased SCN pressure in natto growing regions, there has been more interest in this trait. One line, M13-171089, has done well and we are making foundation seed for this line and it has been sent to several companies for testing. It has good yield, quality, and SCN resistance. There are 201 food-type breeding lines in our program with SCN resistance.

Goals 2. Create elite soybean germplasm with non-88788 sources of SCN resistance so that future soybean growers have more tools in their toolbox to compete with this evolving major pest of soybean.

Objective 2. Advance new sources (non-88788) of SCN resistance and expand the use of these new sources as parents for crossing in the breeding program

During the summer of 2023, 17 successful crosses were made between adapted soybean varieties and breeding lines or exotic accessions carrying putative novel SCN resistance genes. New sources ranged from Peking sources, as well as some new sources from the germplasm collection that appear to be novel. The F1 seeds resulting from these crosses were sent to Chile for generational advancement. F2 populations were successfully generated from these crosses and have been returned from Chile and planted in the St. Paul breeding nurseries for generation advancement. Additionally, we advanced 23 F2 populations and 16 F4 populations segregating for new sources of SCN resistance. The F4 populations were harvested as single plants based on genotype data, threshed, and planted in 2024 as plant rows. We have 1454 new plant rows being grown in 2024 with novel SCN resistance as a result of this project! This is the most I believe we have ever had.

Breeding lines developed from crosses with novel sources of resistance back in 2018 have been advanced to multi-location yield testing. From 806 plant rows with novel resistance planted in 2023, we selected and harvested 102 for preliminary yield testing in 2024. Of the 160 tested in preliminary yield tests in 2022, 66 were advanced to a second year of testing at three locations in 2024.

A recently released variety with Peking-type resistance has been sent out to numerous seed companies for testing and crossing.

Goals 3. Provide an unbiased source of information to growers on the level of SCN resistance in 88788-type commercially available varieties as well as those that have non-88788 sources of resistance.

Objective 3. Conduct SCN bioassays on commercial varieties entering the 2023 UMN Variety Trials using race 3, and conduct bioassays on commercially available non-88788 SCN varieties using races 3 and 14.

We successfully published this report at

https://blog-crop-news.extension.umn.edu/2023/11/soybean-varieties-with-non-88788-scn.html