Project Title: Characterization and Enhancement of Soybean Genetic Resources for Soilborne Disease Resistance.

Principal Investigator: James Kurle (PIs) James Kurle , Xianjin Ma, (Co-PIs)Jim Orf, Nevin Young, Kate Rainey .

Budget Amount and Project Year: $185,237 budgeted for period 10/01/2015 through 9/30/2016. Subcontract to Purdue University of $88,392.

Brief Statement of Objectives: The primary goals of this project are to characterize, identify, and/or isolate novel genes/QTLs conferring resistance or partial resistance to P. sojae, P. ultimum P. irregulare, and F. graminearum, and to deploy the new sources of resistance towards effective disease management in the entire North Central region in coalition of the USB-funded soybean disease research project. We have four research objectives that will help us achieve this goal: 1) Evaluation of soybean germplasm for resistance or partial resistance to P. sojae, P. irregulare, P. ultimum, and F. graminearum; 2) Identification of QTLs underlying resistance to P. sojae, F. graminearum, P. irregulare, and P. ultimum by association mapping; 3) Fine mapping, isolation, and functional verification of two uncharacterized Rps genes conferring resistance to P. sojae; 4) Development of highly adapted soybean cultivars or experimental lines with major resistance QTLs and Rps genes by marker-assisted selection.

Project Summary: (This layman’s summary is the first impression the reviewer gets of a research project) 250 words

U of Minnesota: During this period we: 1) we optimized inoculation techniques for phenotyping for the  four pathogens and tested multiple methods of inoculation with F. graminearum which were conducted to validate the methodology, its effectiveness, and its consistency, to be used to conduct screening for resistance to seed, seedling, and root rot caused by F. graminearum. 2) evaluated 280 early maturity (MG I, 0, and 00) soybean lines ancestral to early MG cultivars developed in Minnesota for partial resistance to two pathogens , P. ultimum var. ultimum, P. irregulare and F. graminearum. Phenotyping for emergence, root rot severity, and change in root and plant weight of inoculated treatments compared with uninoculated controls. Results obtained indicate  that 1) a range of tolerance is present in this collection of soybean lines to the three pathogens and that potential sources of tolerance in the lines can be accessed for use in North Central Regional breeding programs, 2) range of responses to inoculation with these pathogens indicates that tolerance can be found in the regionally adapted lines. The 280 lines were genotyped using 1.5 K & 6.0 K SNP chip. Association mapping is being used to identify markers for tolerance to P. sojae  and F. graminearum based on phenotypic response. Six crosses were made between lines resistant and susceptible to P.sojae for mapping of biparental cross progeny and seed from of the crosses was grown in Chile in 2015-2016 off season nursery

Purdue: Initiated fine mapping to pinpoint location of two genes in smaller genomic regions for isolation of both genes. This would allow more effective selection of each of the two genes in breeding programs. By genotyping and phenotyping of additional progenies we have now narrowed the RpsUN1 from original 1,300 kb to 81kb and RpsUN2 to 64kb from original 430kb. Have begun haplotype analysis comparing this region between PI 567139B and other genotyped soybean accessions to deduce RpsUN1 and RpsUN2 region-unique SNPs for use as molecular markers.  Introgressed RpsUN1 and RpsUN2 into elite breeding lines.

Project Objectives: (Objectives explain the purpose and strategy of the research project and what they are going to do) 250 words

Objective 1: Evaluation of soybean germplasm for resistance or partial resistance to P. sojae, P. irregulare, P. ultimum, and F. graminearum

280 soybean lines ancestral to soybean cultivars developed in Minnesota will be evaluated for resistance or partial resistance to four pathogens in greenhouses and growth chambers, using standardized growing conditions and inoculation techniques to determine varietal reaction to disease pressure.

Objective 2: Identification of QTLs underlying resistance to P. sojae, F. graminearum, P. irregulare, and P. ultimum by association mapping

Genotypic data for the 280 ancestral lines will be analyzed for significant marker-trait association with phenotypic resistance to map markers for resistance or partial resistance.

Objective 3: Fine mapping, isolation, and functional verification of two uncharacterized Rps genes conferring resistance to P. sojae .

PI567139B, possesses excellent resistance to the predominant pathotypes of P. sojae, including those able to defeat the main sources of resistance in contemporary soybean lines.  A study of the resistance in PI567139B identified two potentially new Rps genes, RpsUN1 and RpsUN2. Location of genes will be pinpointed by fine mapping.

Objective 4: Development of highly adapted soybean cultivars or experimental lines with major resistance QTLs and Rps genes by marker-assisted selection

Locally adapted cultivars will be crossed with lines with the two Rps genes and multiple resistance QTLs. Major resistance genes will be identified by marker-assisted selection. Cultivars will also be used in the breeding programs at Purdue and Minnesota for enhancement of resistance in soybean cultivars or  breeding lines.

Project Deliverables: (These are the things you did/delivered/accomplished to meet the objectives for this project) 250 words

Screened 280 ancestral lines for resistance or partial resistance to P. ultimum pv ultimum, P. irregulare (Duplicate runs of rice inoculum assay) and F. graminearum (Duplicate runs - rice inoculum and rolled towel assays). Association mapping of phenotypic data with genotypic detected no significant marker trait associations for partial resistance to F. graminearum. Population size and/or marker density combined with environmental error in measurement of traits resulted in insufficient power to detect significant marker-trait associations

Measures of resistance included reduced root necrosis score and maintenance of relative root weight and relative root length when inoculated plants are compared to uninoculated.  Association mapping detected significant marker associated with reduced root necrosis, relative root weight and root length at a single position and multiple markers for maintenance of relative root dry weight.

As alternative approach to association mapping, six crosses were made between diverse sources, resistant and susceptible lines, for use in biparental mapping. Growout of seed from crosses (F1) will be conducted in South American location to make seed available for 2016 growing season.

Pinpointed location of RpsUN1 to a 6.5-cM region between two SSR markers, Satt159 and 03_0250, on chromosome 3 and RpsUN2 to a 3.0-cM region between 16_1275 and Sat_144 on chromosome 16. Haplotype analysis comparing this region between PI 567139B and other genotyped soybean accessions has identified RpsUN1 and RpsUN2 as unique and are present only in PI567139B.

Introgressed RpsUN1 and RpsUN2 into elite breeding lines.

Progress of Work: (These reports relay the status of each project throughout the lifetime of the project during this fiscal year) 500 words

Objective 1:

Multiple methods of inoculation were tested to validate the methodology to be used to conduct screening for resistance to seed, seedling, and root rot caused by F. graminearum and P. ultimum var.ultimum. Three replicates of 280 lines were also tested for F. graminearum response in growth pouches.  Inoculated plants were assigned a root necrosis score, and the ratio of uninoculated to inoculated root length and root dry weight calculated.  Correlation analysis was performed to compare results in rice inoculated seedling screens and growth pouch assays.  Poor correlations were observed between the seedling and pouch assays for the measured traits.  Growth pouch measurements lack sensitivity effects of F. graminearum inoculation. The rolled towel assay and seedling assay were selected as the most reliable screening methods Phenotyping is underway for three replicates of seedling P. irregulare assay.

We completed six crosses of lines with divergent resistance characteristics, resistant and susceptible, for biparental mapping of resistance and partial resistance to P. sojae. Seed was increased this winter in the Chilean nursery.

To correct possible genotyping errors 40 lines are being regenotyped with the 6k SNP assay.  Once compiled, association mapping will be rerun with all phenotypic data which will improve the power of the tests performed for all traits.

Objective 2:

Association mapping on results of phenotyping for resistance to F. graminearum indicates location of markers for partial resistance to F. graminearum, root necrosis (1 marker identified on chromosome 8) and root rot resistance (10 markers identified which may be good targets for genomic selection) in 280 ancestral lines. Association mapping analysis has begun for 3 replicates of greenhouse P. ultimum var ultimum assays.  Inoculation severely reduced emergence of seedlings. 35% of the 280 lines assayed had no seedlings emerge in any of the three replications. Only three soybean varieties had greater than an average of 50% emergence.  Lack of emergence lessened our ability to assay relative root tolerance, but relative emergence measurements are being mapped in the population and the phenotyping will be repeated at a lower inoculum rate.  Two putative loci were identified on chromosomes 2 and 20.

Objective 3:

Pinpointed location of RpsUN1 and RpsUN2. RpsUN1 was mapped to a 6.5-cM region between two SSR markers, Satt159 and 03_0250, on chromosome 3, suggesting the RpsUN1 was likely to be a novel allele at the Rps1 locus, and RpsUN2 was mapped to a 3.0-cM region between 16_1275 and Sat_144 on chromosome 16, which was also likely to be a novel Rps gene.

Five genes were predicted in the RpsUN1 mapping region as annotated from reference genome (Glyma.Wm82.a2 assembly). Four genes were predicted in the RpsUN2 mapping region as annotated from reference genome (Glyma.Wm82.a2 assembly). All of these genes encode NB-LRR type of genes.

Glyma.03g034600 in the RpsUN1 region showed increased expression after inoculation with P. sojae race 17 while three genes in the RpsUN2 region, Glyma.16g215200, Glyma.16g215000 and Glyma.16g214900, showed increased expression after inoculation with P. sojae race 25. RpsUN1 and RpsUN2 are present only in PI567139B.

Objective 4:

Introgressed RpsUN1 and RpsUN2 into prebreeding lines and elite breeding lines.

Benefit of Soybean Farmers: (This explains the potential impact to farmers based on research project being done) 250 words

The goal of the research described in this project is capitalize on molecular methods to identify and utilize in breeding programs partial resistance to seed and seedling rot pathogens. The potential impact of this research would be to add to the options available to soybean farmers for managing these diseases.The potential benefit for American soybean farmers would be an increase in yield of as much as 10% based on estimates of yield lost to P. sojae and the complex of seedling diseases that include Fusarium and Pythium species.

The research is necessitated by changing patterns in the occurrence of diseases common in the corn-soybean cropping system. Identification of additional highly effect Rps genes are a necessity because of the appearance of new and complex P.sojae pathotypes capable of overcoming currently available resistance genes. Resistance to F. graminearum is necessitated by the increased prevalence of this fungus as a pathogen of soybeans grown in rotation with corn. Resistance to Pythium species is increasingly important as the prevalence of Pythium species that infect both corn and soybean become more common with planting of sequences consisting of only these two crops. Its value would includes assurance of  optimum stand establishment and maintenance of soybean yield by limiting the effect of the soilborne pathogens, P. sojae, F. graminearum, and P. irregular and P. ultimum. Because it would be available as varietal traits incorporated through breeding the benefit would be available at the lowest cost. In addition effective control of seed and seedling rots would insure the value of seed, currently the greatest single expense in soybean production, by protecting against stand loss due to seedling disease. As varietal resistance these traits would also enhance the effectiveness of seed treatment fungicides and management practices intended to limit losses to these diseases.

Performance Metrics: (These are measurement tools we use to measure the success of the project for the association who funded it) 250 words

The success of this project would be indicated by 1) identification of markers for partial resistance to P. sojae, F. graminearum, P. ultimum, and P. irregulare; 2)  incorporation of traits associated with these markers into breeding lines,  3) successful adoption and use of the resistance genes by both public and private breeders for control of the root rots caused by P. sojae, F. graminearum, P. ultimum, and P. irregulare  and 4) adoption of RpsUN1 and RpsUN2 as effective genes for protection against P. sojae in adapted soybean lines grown throughout the North Central Region.

Final Project Results: (This is the final result for the research project for this project year) 500 words

Minnesota

During this project year tests of multiple methods of inoculation with F. graminearum were conducted to validate the methodology, effectiveness, and consistency, to be used to conduct screening for resistance to seed, seedling, and root rot caused by F. graminearum. Based on these tests, the rolled towel assay and rice inoculum method were selected as the most reliable screening methods for assessing root rot and root development.

Utilizing these methods, rolled towel assay and rice inoculum methods, we completed phenotyping and association mapping of first and second runs of screening in 280 ancestral lines for resistance or partial resistance to P. sojae and F. graminearum.

Association mapping analysis was conducted on results obtained in P. sojae and F. graminearum phenotyping indicating the location of markers for partial resistance to F. graminearum. In 280 ancestral lines two categories of marker were identified that indicated resistance to F. graminearum, one marker identified on chromosome 8 indicating resistance to root necrosis and 10 markers associated with reduced susceptibility for reduction in root mass. These markers  may also be good targets for genomic selection for root rot resistance. Association mapping of phenotypic data for P.sojae partial resistance did not detect significant marker train associations for resistance to P. sojae although phenotyping indicated that 280 lines differed widely in response to P.sojae inoculation. To examine this phenomenon more closely we have elected to examine the results of biparental crosses between cultivars exhibiting a wide divergence of responses to P.sojae inoculation. Completed six crosses of lines with divergent resistance characteristics, resistant and susceptible, for use in biparental mapping of resistance and partial resistance to P. sojae.

First run consisting of one rep of evaluation of 280 lines for resistance or partial resistance to P. ultimum is underway.

Purdue:
Generate a higher resolution genetic and physical map and finer mapping of these two genes, RpsUN1 and RpsUN2. RpsUN1 gene has been narrowed from an ~1,300-kb region to an ~150.8-kb region. RpsUN2 gene was narrowed from an ~ 64-kb region down to ~35.6-kb region.

Identify possible candidate genes in the interval region by quantitative real-time PCR gene expression and further analysis of candidate genes in the RpsUN1 and RpsUN2 regions. Expression data demonstrate that only a single gene Glyma.03g034600 in the RpsUN1 region showed enhanced expression pattern after inoculation with P. sojae race 17. By contrast, three genes Glyma.16g215200, Glyma.16g215000 and Glyma.16g214900, in the RpsUN2 region showed enhanced pattern in response to P. sojae race 25. These are candidates for further validation.

Crossed and backcrossed RpsUN1 and RpsUN2 donor lines with four Purdue elite lines, and got the three backcrossing introgression lines with RpsUN1 and RpsUN2 genes, respectively.

Brief State of Next Steps for Project (this is to report what you will be doing next on this project) 250 words

During 2015-2016 research under this grant will focus on:

Minnesota

Evaluate 280 ancestral lines for resistance to P. irregulare and P. ultimum var ultimum and P. ultimum var sporangiferum in controlled environments, greenhouse and growth chamber, assessing for emergence, root rot, ratio of inoculated root to uninoculated root development.

Apply association mapping to phenotype data obtained in evaluation for resistance to P. ultimum var ultimum and P. ultimum var sporangiferum. Identify QTLs associated with favorable, resistant, response to inoculation.

Phenotype and map progeny from biparental cross of P.sojae lines. Conduct biparental crosses of early maturity soybean identified as possessing resistance to F. graminearum, P. irregulare, and P. ultimum var ultimum.

Introgress RpsUN1 and RpsUN2 in MG III lines from Purdue into MG 00, 0, and I lines for use in University of Minnesota soybean breeding program.

Purdue:
Further profile the expression patterns of the candidate genes for RpsUN1 and RpsUN2, isolate the candidate genes for both RpsUN1 and RpsUN2, and validate their function by soybean hairy root transformation and by whole plant transformation simultaneously.

Develop molecular markers from the candidate genes as co-segregating functional markers for most effective introgression of the two genes to elite cultivars.

Continue to backcross the introgression lines with RpsUN1 and RpsUN2 to elite soybean lines for two more generation.

Email report to Sue Heath at sheath@iasoybeans.com